## Slide 1: Team Z Team Project “TaskMaster”
Team Lead: Ben Molloy
Team Member: Brooks Arthur
Team Member: Quay Robinson
Team Member: Cody King
Team Member: Bryce Bien
1

## Slide 2: Project Progress – Overview
Project Burndown:
28 out of 36 (77.7%) requirements complete.
24 out of 48 (50%) tests complete.
Overall Project Completion: 64%
2

## Slide 3: Project Timeline
Milestone 1: Initial Prototype and Canvas Page done.
  Date: 3/24/24
Milestone 2: Each member completes first feature.
  Date: 3/31/24
Deadline 1: Testing, Coding, Documentation of first feature is complete.
  Date: 4/7/24
Milestone 3: Each member completes second feature.
  Date: 4/14/24
Milestone 4: Testing, Coding, Documentation of second feature is complete.
  Due Date: 4/18/24
Deadline 2: Entire Project Should be finished.
  Due Date: 4/21/24
3

## Slide 4: Project Progress – Team Members and Leader
Brooks Arthur: 7 out of 8 requirements complete | 4 out of 7 tests complete
Quay Robinson: 6 out of 7 requirements complete | 3 out of 5 tests complete.
Cody King: 7 out of 8 requirements complete | 6 out of 10 tests complete.
Bryce Bien: 6 out of 9 requirements complete | 3 out of 5 tests complete.
Ben Molloy: 2 out of 4 requirements complete | 4 out of 8 integration tests complete | 4 out of 9 regression tests complete | 0 out of 4 acceptance test complete
4

## Slide 5: Project Progress – Current Milestones Progress
Complete:
Milestone 3: Each member completes second feature.
  Date: 4/14/24
In Progress:
Milestone 4: Testing, Coding, Documentation of second feature is complete.
  Due Date: 4/18/24
5

## Slide 6: Project Progress – Lines Of Code (LoC)
THIS WEEK there were a total of 435 lines of code added to the project:
Ben Molloy: 0
Brooks Arthur: 29
Quay Robinson: 75
Cody King: 48
Bryce Bien: 283
6