## Slide 1: Team Z Team Project “TaskMaster”
Team Lead: Ben Molloy
Team Member: Brooks Arthur
Team Member: Quay Robinson
Team Member: Cody King
Team Member: Bryce Bien
1

## Slide 2: Project Progress – Overview
Project Burndown:
2 out of 36 (6%) requirements complete.
0 out of 48 (0%) tests complete.
Overall Project Completion: 3%
2

## Slide 3: Project Features: Brooks Arthur
Session Controls - To allow for user information to be transferred between pages and saved as cookies in the user's browser.
User Login Page - To allow users to log into there accounts.
3

## Slide 4: Project Features: Quay Robinson
File Upload – To allow users to upload files such as documents to the application.
Tag Query/Search – To allows users to filter and locate tasks within a to-do list based on specific tags assigned to each task.
4

## Slide 5: Project Features: Bryce Bien
Entry Subtasks - To allow users to break down larger tasks into smaller tasks.
Password Encryption and User Data Storage – Implement password encryption and user data storage to ensure the user's information is protected.
5

## Slide 6: Project Features: Cody King
Recurring Entries - To allow users to create tasks that will occur regularly, so the user will have the option to have a task repeated daily, weekly, monthly, or yearly.
Search By Date – To allow users to efficiently locate tasks by specific dates or within a range of dates.
6

## Slide 7: Project Timeline
Milestone 1: Initial Prototype and Canvas Page done.
  Date: 3/24/24
Milestone 2: Each member completes first feature.
  Date: 3/31/24
Deadline 1: Testing, Coding, Documentation of first feature is complete.
  Date: 4/7/24
Milestone 3: Each member completes second feature.
  Date: 4/14/24
Milestone 4: Testing, Coding, Documentation of second feature is complete.
  Due Date: 4/21/24
Deadline 2: Entire Project Should be finished.
  Due Date: 4/28/24
7

## Slide 8: Project Progress – Team Members and Leader
Brooks Arthur: 0 out of 8 requirements complete | 0 out of 7 tests complete
Quay Robinson: 0 out of 7 requirements complete | 0 out of 5 tests complete.
Cody King: 0 out of 8 requirements complete | 0 out of 10 tests complete.
Bryce Bien: 0 out of 9 requirements complete | 0 out of 5 tests complete.
Ben Molloy: 2 out of 4 requirements complete | 0 out of 8 integration tests complete | 0 out of 9 regression tests complete | 0 out of 4 acceptance test complete
8

## Slide 9: Project Progress – Current Milestones Progress
Complete:
Milestone 1: Initial Prototype and Canvas Page Done.
  Due Date: 3/24/24
In Progress:
Milestone 2: Each member completes first of two features.
  Due Date: 3/31/24
9

## Slide 10: Project Progress – Lines Of Code (LoC)
There were a total of 659 lines of code added to the project this week:
Ben Molloy: 659
Brooks Arthur: 0
Quay Robinson: 0
Cody King: 0
Bryce Bien: 0
10